## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | PB1 | As a system, we want to set up Neo4j, LangChain, and the React environment and connect to ISRO datasets (CSV, PDF, Kaggle) so that mission data can be processed automatically. This ensures a scalable foundation for building the ISRO Mission Knowledge Graph from structured and unstructured sources. | MUST HAVE | No Dependency | Mayureshwar Shendre | 3- Completed
S1 | S1 | PB2 | As a data engineer, I want to load ISRO satellite, rocket, and launch datasets, clean duplicates, and normalize mission names so that the graph maintains consistency. This guarantees accurate downstream entity extraction and reliable relationship mapping. | MUST HAVE | Project Foundation and environment configuration. | Mayureshwar Shendre | 3- Completed
S2 | S2 | PB3 | As an AI engineer, I want to automatically extract Satellite, Rocket, Scientist, Mission, and Launch Site entities from ISRO data to eliminate manual tagging. This enables structured triple generation for building a dynamic knowledge graph. | MUST HAVE | Cleaned and normalized data from Data Ingestion Layer. | Mayureshwar Shendre | 3- Completed
S2 | S2 | PB4 | We want structured triples (Satellite–launched_by–Rocket, Mission–orbit_type–LEO) stored in Neo4j so that ISRO relationships become easily queryable. This allows advanced Cypher queries and real-time exploration of mission connections. | SHOULD HAVE | Entity & Relationship Extraction | Mayureshwar Shendre | 3- Completed
S2 | S2 | PB5 | As a system architect, I want to combine mission year, launch vehicle, orbit type, and mission purpose into enriched node properties so that AI retrieval becomes context-aware. This improves reasoning accuracy in the RAG-based question-answering system. | MUST HAVE | Graph Construction and validated node properties | Mayureshwar Shendre | 3- Completed
S3 | S3 | PB6 | As a system, I want to generate semantic vector embeddings for ISRO missions and documents using transformer models so that deeper mission relationships are captured. This enables intelligent similarity search across historical and upcoming missions. | MUST HAVE | Rich Context Engineering and structured data storage. | Mayureshwar Shendre | 3- Completed
S3 | S3 | PB7 | As a developer, I want to build a native Neo4j vector index for ISRO mission embeddings so that we can perform semantic search without relying on external vector databases. This simplifies architecture while maintaining high-performance retrieval. | MUST HAVE | Embedding Generation must be completed. | Mayureshwar Shendre | 3- Completed
S3 | S3 | PB8 | As a decision-maker, we want contextual Q&A over ISRO mission data using a Graph-RAG pipeline so that answers are fact-grounded and relationship-aware. This ensures accurate insights like mission chronology, rocket evolution, and future program connections. | MUST HAVE | Vector Indexing and operational Knowledge Graph. | Mayureshwar Shendre | 3- Completed
S4 | S4 | PB9 | As a project stakeholder, I want a web-based interactive dashboard displaying total missions, rockets used, orbit distribution, and success rates in real time. This provides a visual exploration of the ISRO Mission Knowledge Graph. | MUST HAVE | Graph Database and RAG API must be operational. | Mayureshwar Shendre | 3- Completed
S4 | S4 | PB10 | As a non-technical user, I want an AI-powered chat interface to ask questions like “Which rocket launched Chandrayaan-3?” in plain English. This eliminates the need to write Cypher queries and makes the system accessible to students and researchers. | MUST HAVE | Graph RAG Pipeline must be fully integrated with backend APIs | Mayureshwar Shendre | 3- Completed
S4 | S4 | PB11 | As an administrator, I want the ISRO Knowledge Graph platform securely deployed with protected API keys and database credentials so that it is safely accessible online. This ensures reliable public demonstration and remote stakeholder access. | SHOULD HAVE | Dashboard, RAG Pipeline, and Graph Database must be fully tested and stable. | Mayureshwar Shendre | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 120 | 71 | 52 | 52 | 53 | 50 | 38 | 28 | 17 | 5 | 3 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T1 | Setup Neo4j, LangChain, HuggingFace & project environment | 2026-01-05 | 2026-01-06 | Mayureshwar Shendre and Niranjan Patil | Build | Completed | 11 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T2 | Load ISRO Satellite CSV & Kaggle datasets | 2026-01-06 | 2026-01-08 | Mayureshwar Shendre and Niranjan Patil | Coding | Completed | 9 | 4 | 4 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T3 | Data cleaning (duplicate removal, rocket normalization PSLV/GSLV/LVM3) | 2026-01-08 | 2026-01-12 | Mayureshwar Shendre and Niranjan Patil | Coding + Unit Test | Completed | 12 | 5 | 5 | 4 | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T4 | Define Knowledge Graph schema (Satellite–Rocket–Mission–Scientist) | 2026-01-10 | 2026-01-14 | Mayureshwar Shendre and Niranjan Patil | Design | Completed | 8 | 8 | 3 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T5 | Develop ISRO-specific entity extraction module | 2026-01-19 | 2026-01-23 | Mayureshwar Shendre and Niranjan Patil | Coding | Completed | 10 | 4 | 5 | 4 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T6 | Generate triples (Satellite–launched_by–Rocket) | 2026-01-21 | 2026-01-26 | Mayureshwar Shendre and Niranjan Patil | Coding + Integration Test | Completed | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T7 | Implement Neo4j graph creation using MERGE + constraints | 2026-01-23 | 2026-01-28 | Mayureshwar Shendre and Niranjan Patil | Build + System Test | Completed | 8 | 0 | 0 | 3 | 5 | 4 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T8 | Create Rich Context properties for graph nodes | 2026-02-02 | 2026-02-05 | Mayureshwar Shendre and Niranjan Patil | Design + Coding | Completed | 5 | 4 | 4 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T9 | Generate embeddings using HuggingFace MiniLM | 2026-02-04 | 2026-02-08 | Mayureshwar Shendre and Niranjan Patil | Coding | Completed | 7 | 7 | 4 | 5 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T10 | Implement Neo4j native vector index | 2026-02-06 | 2026-02-11 | Mayureshwar Shendre and Niranjan Patil | Integration Test | Completed | 10 | 7 | 5 | 4 | 3 | 5 | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T11 | Build Graph RAG pipeline with Llama-3 | 2026-02-07 | 2026-02-11 | Mayureshwar Shendre and Niranjan Patil | Build + System Test | Completed | 5 | 7 | 3 | 2 | 5 | 5 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T12 | Develop React-based ISRO Graph Dashboard | 2026-02-16 | 2026-02-20 | Mayureshwar Shendre and Niranjan Patil | Build + UI Design | Completed | 12 | 5 | 5 | 5 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T13 | Integrate Backend API with Neo4j & RAG | 2026-02-18 | 2026-02-22 | Mayureshwar Shendre and Niranjan Patil | Integration Test | Completed | 8 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T14 | Cloud Deployment (Neo4j AuraDB + Vercel/Render) | 2026-02-20 | 2026-02-24 | Mayureshwar Shendre and Niranjan Patil | Deployment | Completed | 9 | 8 | 0 | 0 | 3 | 4 | 4 | 4 | 4 | 5 | 3 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Project Discussion & ISRO Data Preprocessing: Needed a robust strategy to handle inconsistent ISRO datasets (duplicate satellite names, mixed rocket naming like PSLV-XL vs PSLV, date format inconsistencies) before feeding into the graph pipeline. | Discussed data normalization strategy; implemented automated preprocessing script using Pandas for duplicate removal, date standardization, and rocket name harmonization.
Sprint 1 | Day 6 | Data Cleaning Issue: Trailing whitespaces and inconsistent capitalization in satellite and rocket names were creating duplicate nodes in Neo4j. | Refactored ingestion pipeline with strict .strip(), .lower(), and canonical mapping logic to ensure consistent node creation in Neo4j.
Sprint 2 | Day 12 | Entity Extraction Challenge: Difficulty in defining extraction logic for ISRO-specific entities (Satellite, Rocket, Scientist, Launch Site, Mission Year) from semi-structured datasets and PDF documents | Refined entity_extractor module; designed ISRO-specific NER prompts and mapping rules to generate structured triples (Satellite–launched_by–Rocket).
Sprint 2 | Day 18 | Graph Modeling Bottleneck: Cypher queries were causing duplicate relationships and inefficient graph construction due to improper CREATE usage. | Revised Cypher queries using MERGE with constraints and indexes; enforced uniqueness constraints on Satellite and Rocket nodes.
Sprint 3 | Day 25 | Embedding Strategy Finalization: Needed a semantic vectorization strategy to capture contextual meaning of mission descriptions instead of simple keyword matching. | Integrated Hugging Face MiniLM model to generate high-dimensional embeddings for ISRO mission data; validated semantic similarity results.
Sprint 3 | Day 30 | Vector Indexing Issue: Neo4j native vector index was retaining stale embeddings during iterative updates, affecting search accuracy. | Implemented automated DROP & RECREATE index sequence; ensured embedding refresh during each data update cycle.
Sprint 4 | Day 40 | Context Engineering Problem: Graph RAG pipeline produced fragmented answers due to insufficient contextual node properties, causing minor hallucinations. | Designed “Rich Context” node property combining mission purpose, orbit type, launch date, and success status; optimized prompt engineering for grounded responses.
Sprint 4 | Day 45 | Deployment Bottleneck: Cloud deployment failed due to heavy ML dependencies increasing memory usage beyond platform limits. | Optimized backend by switching to CPU-only Torch build, minimized dependency footprint, and deployed Neo4j AuraDB + lightweight API server successfully.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-12-29 | 2026-01-16 | Mayureshwar Shendre and Niranjan Patil | Implementing strict ISRO dataset validation rules (.strip(), canonical rocket mapping like PSLV/GSLV/LVM3, date normalization) early in the ingestion pipeline. | Underestimating inconsistencies in ISRO satellite datasets such as mixed rocket variants (PSLV-XL vs PSLV) and duplicate mission entries. | Pair-programming for ingestion logic refinement and conducting daily schema review sync meetings. | Designed a robust Pandas-based preprocessing framework for ISRO data cleaning, duplicate removal, and rocket name standardization before graph construction.
2 | Sprint 2 | 2026-01-19 | 2026-01-30 | Mayureshwar Shendre and Niranjan Patil | Testing Cypher queries directly in Neo4j Browser before integrating them into Python scripts for graph population. | Using CREATE statements that caused duplicate Satellite and Rocket nodes during iterative graph loading. | Maintaining a clear ontology design (Satellite, Rocket, Mission, Scientist, Launch Site) and documenting relationships like launched_by and managed_by. | Replaced CREATE with MERGE clauses, implemented uniqueness constraints, and finalized the ISRO Knowledge Graph schema to ensure idempotent node creation.
3 | Sprint 3 | 2026-02-02 | 2026-02-13 | Mayureshwar Shendre and Niranjan Patil | Engineering “Rich Context” node properties combining mission purpose, orbit type, launch date, and success status before embedding generation. | Relying on outdated Neo4j vector indexes during iterative embedding experiments. | Leveraging native Neo4j vector indexing for semantic search instead of introducing unnecessary external FAISS dependencies. | Implemented DROP & RECREATE index automation and successfully integrated the Hybrid Graph RAG retrieval pipeline using Llama-3.
4 | Sprint 4 | 2026-02-16 | 2026-02-23 | Mayureshwar Shendre and Niranjan Patil | Reviewing cloud deployment constraints (Neo4j AuraDB + lightweight backend API + React frontend) before finalizing dependency configuration. | Tracking large local environment files and unnecessary ML packages in version control. | Refining Llama-3 prompt engineering and improving retrieval grounding logic for more accurate ISRO mission Q&A. | Optimized backend dependencies (CPU-only Torch build), secured environment variables, and successfully deployed the ISRO Mission Knowledge Graph dashboard.